## Sheet1
MUSIC STORE DATABASE
|  | Task title | Priority | Start Date | Due Date | PCT of task complete | Comments
| 1) | Design Database | High | 6 April,2019 | 7 April,2019 | 100% | It was Hard to figure out reltionships of tables.
| 2) | Model Creation | High | 8 April,2019 | 9 April,2019 | 100% | time consuming to set foreignkeys.
| 3) | Data insertion | High | 11 April,2019 | 12 April,2019 | 100% | Someimes there was becoming a problem of inserting a appropriate data.
| 4) | Queries | High | 13 April,2019 | 13 April,2019 | 100% | It was easy to create the queries.
| 5) | Views and stored procedures | Medium | 13 April,2019 | 13 April,2019 | 100% | difficult to create
| 6) | Documentation | Medium | 14 April,2019 | 14 April,2019 | 100% | easy
| 7) | ppt and excel sheet | Medium | 14 April,2019 | 14 April,2019 | 100% | easy